## PBL
No. | Product Backlog Items | Values |  | Initial Size Estimate | New Estimate at Sprint
|  | Sprint#1 | Sprint#2 | 0 | 1 | 2 | 3 | 4 | 5
Bug Fix
1 | The system can no longer connect to the APIs/retrieve the information from the API of the major publications DB such as WOS, SCOPUS, Google Scholar, and TCI | 40000 | 40000
2 | The system presents incorrect information of the researchers in the College of Computing. The researchers are group in the research labs they are not belong to. | 40000 | 40000
3 | The visualization of the publication status is netheir match to what is on Google Scholar nor SCOPUS. | 40000 | 40000
Researcher
4 | As a researcher, I want a complete report on my publications so that I can attach the report with my CV or yearly evaluation form. | 20000 | 20000
5 | As a researcher, I want to keep my information up-to-date. | 20000 | 20000
6 | As a researcher, I want to create a call for research assistant, Ph.D., and postdoctoral researcher as needed. | 20000
17 | As a head of a research group, I want to create a call for research assistant, Ph.D., and postdoc vacancies available to apply with terms and conditions. | N/A | 20000
18 | As an authorized researchers, I want to keep the lab information up-to-date. | N/A | 20000
7 | As a researcher, I want to keep the research lab information up-to-date. | 20000
Administrative staff
8 | As an administrative staff, I want to keep the project funding information up-to-date. | 20000 | 20000
9 | As an administrative staff, I want to present the highlights to all visitors. | 20000 | 20000
10 | As an administrative staff, I want to create a report to support the decision of the executive board. | 30000 | 20000
11 | As an administrative staff, I want to assist the researcher to make their research works and publications up-to-date. | 20000 | 20000
System admin
12 | As an admin, I want to see the log the system | 20000
19 | As an admin, I want a dashboard of user's actities log, error log, and important system information log. | N/A | 30000
13 | As an admin, I want a report of user's activitities in the system, so that I can plan better. | 20000 | 20000
14 | As an admin, I want to update all of the information on behalf of a user. | 20000 | 20000
All users
15 | As a user, I want to check on information of each lab and each researcher. | 10000 | 10000
16 | As a user, I want to switch language at all time. | 10000 | 10000
| Total | 350000 | 350000